## Sheet1
PROJECT CHARTER
1 | Project Name |  | Project Sponsor | Project Manager |  | Reference
| Increase market share |  | C.T. Wilson | Poh William |  | SDE/0023
2 | Process |  |  | Manufacturing process of die-casting
Process selected for improvement:
3 | Goal Statement |  |  | To recapture 10% incremental market share by outperforming competitors in terms of faster delivery and improved quality by June-2007
Purpose and goals of the project:
4 | Objective |  | Parameter | Measure |  | Baseline (now) | Goal (future) |  | Unit of Measure
Key metrics of the project:
|  |  | Delivery Time | Why late? List reason for each occurrence. |  | 6 | 4 |  | days
|  |  | Customer Reject Rate | Why rejected? Group rejects into 5 groups. |  | 0.1 | 0.01 |  | % shipped
|  |  | Scrap Rate | Why scrapped? Group scrap into 5 groups. |  | 10 | 2 |  | % produced
5 | Cost/Benefit |  | Initial Expectations | Business Case |  | Comments
| Capital costs |  | 350000 |  |  | Software and hardware upgrade
| Operating costs |  | 450000 |  |  | Retraining and education; One new truck; additional 2 trips/day
| Operating benefits |  | 1200000 |  |  | Increase revenue, market share, higher customer satisfaction
| Cost-Benefit Total |  | 400000
6 | Return/Value |  | Parameters | Impact of Improvement |  |  |  |  | Return
Expected financial impact:
|  |  | Delivery Time | 2 weeks faster delivery = 15% more orders |  |  |  |  | $150k
|  |  | Customer Reject Rate | 10x reduced rejects = retaining more customers = 20% higher order volume |  |  |  |  | $200k
|  |  | Scrap Rate | 5x reduced scrap rate = product-cost reduced from $550k to $510k |  |  |  |  | $40k
7 | Customer benefit |  |  | Faster delivery and lower defect rate, lower total cost, higher satisfaction.
Improvement that the customer will notice:
8 | Team |  | Names | Function | Responsibility
Names and responsibilities:
|  |  | James | Quality Manager | Analyze reject-rate in OQC over past 12 mths, list top 5 reasons.
|  |  | Nguyen, Wong | Marketing Manger & Customer Acct Mgr | Define lost orders (value) due to rejects.
|  |  | Nick | Cost Accountant and Controller | Summarize value of customer rejects
|  |  | Rick | Production Manager | Account scrap by (1) assembly (2) material (3) test (4) visual.
|  |  | Freddy | Process Engineer | Update drawings/procedures to minimize assembly errors.
9 | Scope |  |  | Included: technical production process. Excluded: sales and human resources.
Project scope, what is included, what is excluded:
10 | Schedule |  | Project-Phase | Deliverables | Responsible |  |  | Date
Item and completion dates:
|  |  | Define | Project Charter | James |  |  | 2007-03-22
|  |  | Measure | Baseline Capabilities | James |  |  | 2007-03-29
|  |  | Analyze | Analysis + Action Plan | James, Nick |  |  | 2007-04-05
|  |  | Improve | Improvements | Rick |  |  | 2007-04-20
|  |  | Control | Control Plan | Freddy |  |  | 2007-04-27
11 | Support
Needs for project-execution:
Note on K51: Define Project Charter: - Schedule - Deliverables - Responsibilities
Note on K53: Measure - Map the Process - Baseline Capabilities
Note on K55: Analyze - Organize data - Cause & Effect - Control Charts - Summarize findings - Create Action Plan
Note on K57: Improve - Eliminate failures (FMEA) - Optimize processes (DOE)
Note on K59: Control - Control Plan - Control Charts
Note on R7: Description - State one goal only - Describe goal precisely