## Sheet1
Stakeholder and Barrier To Change Analysis
Closeness To Customer Improvement
Stakeholder |  | Stakeholder interest in the project | Influence and Power | Interest | Strategies/ Communication Plan
1 | Marketing VP | Affecting the functions and deliverables | 0 | 3 | Bi-weekly status meetings and copy on project executive review
2 | Engineering VP | Responsible for manufacturing process ownership, and owns the metrics | 2 | 4 | Bi-weekly status meetings and copy on project executive review
3 | Operations Director | Provides resources and will be owner of the new process | 4 | 4 | Bi-weekly status meetings and copy on project executive review
Barrier to change |  | Project Implication | Solution
1 | New Product Introduction activities consume resources | Unable to get the right team membership | Determine the outlook on NPI, and requires additional headcount to cover additional assignment
2 | Availability of training resources | Lack of the required skill-level and need intensive training | Discuss status quo with HR and training functions
Interest
Power
Low (-5)
Low (-5)
High (+5)
High (+5)
X Marketing VP
X Marketing VP
X Operations Director
Monitor
(with minimum effort)
Keep
Informed
Managed
Closely
Keep
Satisfied
The stakeholder's position on the grid shows you the actions you have to take with them:
● High power, interested people: these are the people you must fully engage with, and make the greatest efforts to satisfy.
● High power, less interested people: put enough work in with these people to keep them satisfied, but not so much that they become bored with your message.
● Low power, interested people: keep these people adequately informed, and talk to them to ensure that no major issues are arising. These people can often be very helpful with the detail of your project.
● Low power, less interested people: again, monitor these people, but do not bore them with excessive communication.